## Sheet1
Risk Plan for Language Learners United over 9000
Team members are Michael Cottrell and Riley Tucker
Risk Table
Risk Number | Risk Summary | Risk Category | Probablility | Impact (1-4) | Priority
1 | Michael must withdraw from the semester | Management Risk | 1 | 4 | 1
2 | Riley Must withdraw from the semester | Management Risk | 1 | 4 | 1
3 | Wikipedia or its API is removed | Technical Risk | 1 | 4 | 1
4 | Flash Card Word API removed | Technical Risk | 1 | 4 | 1
5 | Inexperience causing code delay | Technical Risk | 4 | 2 | 4
6 | Separate Databases causes issues in coding | Technical Risk | 6 | 2 | 6
7 | No centralized website for testing causes issues in coding | Technical Risk | 6 | 2 | 6
8 | Michael or Riley are ill during critical stages | Management Risk | 4 | 2 | 4
9 | No centralized hardware causes code to not run properly on Michael's and Riley's machine | Technical Risk | 8 | 2 | 8
10 | Size of software is understimated | Technical Risk | 6 | 3 | 6
11 | Michael or Riley's computer is inoperable | Technical Risk | 1 | 4 | 1
Actions
Risk Number | Action to take
1 | Riley has to take over the project, or joins another group and this project is scrapped.
2 | Michael has to take over the project, or joins another group and this project is scrapped.
3 | Project will require a different or multiple different sources. Or facts about languages will need to be researched and manually inserted into database.
4 | Project will require a different or multiple different sources. Or words will need to be researched and manually inserted into database.
5 | Research and use any available tools to help learn how to solve the coding issues.
6 | Work on debugging differences in the database. Make to have default scripts for database to match crucial data between database instances.
7 | Work on debugging differences in code needed or different libraries missing.
8 | Seek or buy appropiate medical care to diminish illness time, meanwhile other member will pickup slack.
9 | Work on debugging differences in code needed or different libraries missing.
10 | Start coding early and often.
11 | If possible repair or buy a new computer, otherwise other member will have to pickup slack.